## Sheet1
HKLCF Full-Proposal Work Plan Template
2024 (Add as many months and years necessary)
Objectives and Activities (Enter as many as you like) | January | February | March | April | May | June | July | August | September | October | November | December | Outcomes*
Objective 1: | 2024 (Add as many months and years necessary) January: <------- Objectives equate to Outcomes -------> | Outcome X: (as listed in your proposal)
Activity 1: | 2024 (Add as many months and years necessary) January: <------- Actvities equate to Performance Measures -------> | Performance Measure A: (as listed in your proposal)
Activity 2: | [12 empty] | Performance Measure A: (as listed in your proposal)
Activity 3: | [12 empty] | Performance Measure B: (as listed in your proposal)
Objective 2: | [12 empty] | Outcome Y: (as listed in your proposal)
Activity 4:
Activity 5:
Activity 6:
*note objectives can filter into fewer outcomes. Performance measures and outcomes may be used more than once (see sample)
HKLCF Full-Proposal Work Plan Template SAMPLE
*Highlight colors and other rendering is entirely at applicant's discretion
2024
Objectives and Activities | January | February | March | April | May | June | July | August | September | October | November | December | Outcomes
Objective 1: X lbs. of invasive species | 2024 Outcomes: Z acres of reef flat restored by reducing invasive species cover to <5% in the area
Activity 1: Gather supplies for removal | 2024 Outcomes: Organizational capacity is increased with supplies for this and future projects
Activity 2: Community removal events (to be held every other month | 2024 Outcomes: 6 community events held involving over 200 volunteers removing and recycling X lbs. of invasive species
Activity 3: Deliver removed inavsives to composting facility (following every 2 removal efforts) | 2024 Outcomes: 6 community events held involving over 200 volunteers removing and recycling X lbs. of invasive species
Objective 2: outplant Y # of native species in the removal area | 2024 Outcomes: Z acres of reef flat restored by outplanting native species at R density in the area
Activity 4: Train small group of community participants on outplant process | 2024 Outcomes: 10 volunteers from within community trained in native species outplanting protocol
Activity 5: Collect native species to be outplanted | 2024 Outcomes: Y # native species outplanted at removal sites
Activity 6: Outplant natives following each community removal event | 2024 Outcomes: Y # native species outplanted at removal sites